## README
101 Okey — Development Plan & Task Tracker
How to use this workbook
1) Go to Settings: set Project Start Date, and optionally edit the dropdown lists. 2) Go to Tasks: this is the master backlog. Filter by Stage/Status/Priority and feed tasks to Codex. 3) Use the Notes / Codex Prompt Seed column as the starting prompt when delegating a task. 4) Go to Dashboard for progress charts; Gantt for the stage timeline. Workflow suggestion: - Keep tasks in Backlog until you’re ready; then set Status=Planned and assign a Start Offset. - When you start coding, set Status=In Progress. Use Blocked when waiting on dependencies. - Mark Done only when Acceptance Criteria is met on both PC and Android (when applicable). Online multiplayer is planned using Epic Online Services (EOS) P2P with guest (DeviceID) login by default. Some networks can still fail; we also keep LAN/direct-connect as a fallback mode.

## Settings
Project Settings
Project Name | 101 Okey (Godot)
Project Start Date | 2026-02-03
Sprint Length (days) | 14
Default Turn Timer (sec) | 60
Default Match Mode | Target Score
Default Target Score | 101
Default Rounds | 8
Animation Speed | Normal
Tips Verbosity | OnboardingOnly
Online Identity | GuestDeviceID
Dropdown Lists (edit if needed)
Status | Priority | Type | Platform | Owner | Stage | Bot Personality | Difficulty
Backlog | P0 | Design | All | You | 0 - Preproduction (Spec & Design Lock) | Random | Easy
Planned | P1 | Engineering | Offline | Codex | 1 - Project Setup & Tooling | Aggressive | Medium
In Progress | P2 | Art | Online | You+Codex | 2 - Core Game Engine (Rules/State) | Conservative | Hard
Blocked |  | Audio | PC | TBD | 3 - Offline Gameplay Loop | Chaotic
Review |  | QA | Android |  | 4 - UI/UX & Input
Done |  | DevOps |  |  | 5 - Bots (AI)
|  | Writing |  |  | 6 - Online Multiplayer (EOS + P2P)
7 - Reconnect & Resilience
8 - Polish (Audio/Accessibility/Perf)
9 - QA & Test Matrix
10 - Builds & Release Pipeline
11 - Store/Distribution Prep

## Tasks
ID | Epic | Feature | Task | Description | Stage | Type | Platform | Priority | Est (hrs) | Est (days) | Dependencies | Owner | Status | Start Offset (d) | Start Date | End Date | Notes / Codex Prompt Seed | Acceptance Criteria
T-0001 | Preproduction | Ruleset | Write Classic TR 101 rules specification | Document full TR 101 Okey rules: tiles, indicator/okey, dealing, turns, opening, scoring, end-of-round, penalties. | 0 - Preproduction (Spec & Design Lock) | Design | All | P0 | 10 | 2 |  | You+Codex | Backlog | 0 | 2026-02-03 | 2026-02-04 | Ask Codex to draft a rules spec doc based on Turkish 101 Okey; verify manually. | A single source-of-truth rules spec exists and is reviewed; ambiguous points resolved.
T-0002 | Preproduction | Ruleset | Define house-rule toggles + presets list | Decide safe modular toggles (timer, match target, opening threshold, scoring multipliers) and 3-5 presets. | 0 - Preproduction (Spec & Design Lock) | Design | All | P0 | 6 | 1 |  | You+Codex | Backlog | 1 | 2026-02-04 | 2026-02-04 |  | RuleConfig v1 list finalized; no toggle changes core tile mechanics.
T-0003 | Preproduction | Architecture | Define GameState schema + action API | Define data model (Tile, PlayerState, GameState) + all legal actions with payloads. | 0 - Preproduction (Spec & Design Lock) | Design | All | P0 | 8 | 2 |  | You+Codex | Backlog | 1 | 2026-02-04 | 2026-02-05 |  | Action list covers all gameplay; each action maps to validation + apply.
T-0004 | Preproduction | Architecture | Networking event flow (host-authoritative) | Define online flow: host validates intents, broadcasts deltas, resync snapshots, reconnect, AI takeover. | 0 - Preproduction (Spec & Design Lock) | Design | Online | P0 | 6 | 1 |  | You+Codex | Backlog | 2 | 2026-02-05 | 2026-02-05 |  | Sequence diagrams for normal play + reconnect; no undefined states.
T-0005 | Preproduction | UX | Wireframe core screens | Wireframe: Main Menu, Offline Setup, Online Lobby, Table, Round Summary, Settings. | 0 - Preproduction (Spec & Design Lock) | Design | All | P0 | 8 | 2 |  | You+Codex | Backlog | 2 | 2026-02-05 | 2026-02-06 |  | Wireframes cover all actions; Android landscape considered.
T-0006 | Preproduction | Art | Visual style mini moodboard | Pick flat 2D style references for tiles/table; define fonts, spacing, color palette, icon style. | 0 - Preproduction (Spec & Design Lock) | Design | All | P1 | 4 | 1 |  | You+Codex | Backlog | 3 | 2026-02-06 | 2026-02-06 |  | Style guide page with tile mock + UI colors.
T-0007 | Preproduction | Backlog | Create task board + definitions | Define status workflow, priority rules, definition of done, branching strategy. | 0 - Preproduction (Spec & Design Lock) | Design | All | P1 | 3 | 1 |  | You+Codex | Backlog | 3 | 2026-02-06 | 2026-02-06 |  | Workflow documented; tasks ready for execution.
T-0008 | Setup | Repo | Initialize repository + .gitignore + LFS (if needed) | Create repo, ignore Godot artifacts, decide if LFS needed for art. | 1 - Project Setup & Tooling | DevOps | All | P0 | 2 | 0.5 |  | You+Codex | Backlog | 4 | 2026-02-07 | 2026-02-07 |  | Repo exists; clean status after opening project.
T-0009 | Setup | Godot | Create Godot 4 project structure | Setup scenes, scripts, autoloads folders, naming conventions. | 1 - Project Setup & Tooling | Engineering | All | P0 | 4 | 1 |  | You+Codex | Backlog | 4 | 2026-02-07 | 2026-02-07 |  | Project opens; folders reflect architecture; autoload stubs.
T-0010 | Setup | Tooling | Configure code formatting & linting | Adopt GDScript style guidelines; pre-commit hooks optional. | 1 - Project Setup & Tooling | DevOps | All | P1 | 4 | 1 |  | You+Codex | Backlog | 5 | 2026-02-08 | 2026-02-08 |  | Formatter/linter runs; CI step (if used) passes.
T-0011 | Setup | Build | Android export setup + keystore placeholders | Configure Android export template, input, orientation landscape, signing placeholders. | 1 - Project Setup & Tooling | DevOps | Android | P0 | 6 | 1 |  | You+Codex | Backlog | 5 | 2026-02-08 | 2026-02-08 |  | Can export and run a blank build on Android device/emulator.
T-0012 | Setup | Build | PC export presets | Configure Windows/Linux export presets and basic packaging. | 1 - Project Setup & Tooling | DevOps | PC | P1 | 3 | 0.5 |  | You+Codex | Backlog | 5 | 2026-02-08 | 2026-02-08 |  | Can export and run on PC.
T-0013 | Setup | Infra | Logging + debug overlay | Add logging utility and optional on-screen debug panel for state, network, FPS. | 1 - Project Setup & Tooling | Engineering | All | P1 | 6 | 1 |  | You+Codex | Backlog | 6 | 2026-02-09 | 2026-02-09 |  | Logs written; debug overlay toggles via key/gesture.
T-0014 | Setup | QA | Lightweight test harness scaffolding | Create test scene/scripts to run pure rules tests quickly. | 1 - Project Setup & Tooling | QA | All | P1 | 6 | 1 |  | You+Codex | Backlog | 6 | 2026-02-09 | 2026-02-09 |  | Can run tests headless or via scene; produces pass/fail output.
T-0015 | Engine | Rules | Implement Tile model + constants | Tile representation: color, number, okey, fake okey; helpers for equality/serialization. | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 4 | 1 | T-0003 | You+Codex | Backlog | 7 | 2026-02-10 | 2026-02-10 |  | Tiles serialize/deserialize; unit tests for identity.
T-0016 | Engine | Rules | Implement deck generation + shuffle by seed | Create full tile set; shuffle deterministically via seed; expose seed in GameState. | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 6 | 1 | T-0003 | You+Codex | Backlog | 7 | 2026-02-10 | 2026-02-10 |  | Given same seed, deck order identical across runs.
T-0017 | Engine | Rules | Implement dealing logic | Deal initial hands according to TR rules (including extra tile to starting player). | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 6 | 1 | T-0001, T-0003, T-0010 | You+Codex | Backlog | 8 | 2026-02-11 | 2026-02-11 |  | Hands sizes correct; indicator set; discard initialized.
T-0018 | Engine | State | Define GameState + PlayerState classes | Implement pure data objects and cloning/copy utilities. | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 6 | 1 | T-0003 | You+Codex | Backlog | 8 | 2026-02-11 | 2026-02-11 |  | State can deep-copy; no shared references.
T-0019 | Engine | Actions | Implement action validation framework | validate_action(state, player, action, rules) returns ok + reason code. | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 10 | 2 | T-0003, T-0011 | You+Codex | Backlog | 9 | 2026-02-12 | 2026-02-13 |  | Every action returns deterministic result; reasons enumerated.
T-0020 | Engine | Actions | Implement apply_action reducer + event log | apply_action returns new_state + delta/events (for UI + network). | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 10 | 2 | T-0016 | You+Codex | Backlog | 10 | 2026-02-13 | 2026-02-14 |  | Reducer is pure; events sufficient to animate UI.
T-0021 | Engine | Rules | Implement scoring engine | Compute points for open melds, penalties, end-of-round scoring; support match targets. | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 12 | 3 | T-0001, T-0002, T-0017 | You+Codex | Backlog | 11 | 2026-02-14 | 2026-02-16 |  | Score matches spec; unit tests for sample rounds.
T-0022 | Engine | Rules | Implement RuleConfig + presets + hashing | RuleConfig object with preset id + overrides; stable hash for online lobby. | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 8 | 1.5 | T-0002 | You+Codex | Backlog | 10 | 2026-02-13 | 2026-02-14 |  | Config serializes; hash stable; presets load.
T-0023 | Engine | Serialization | State snapshot + delta serialization | Serialize GameState and delta/events to JSON or packed bytes for network/resync. | 2 - Core Game Engine (Rules/State) | Engineering | Online | P0 | 10 | 2 | T-0014, T-0017 | You+Codex | Backlog | 12 | 2026-02-15 | 2026-02-16 |  | Snapshot round-trips; delta apply works.
T-0024 | Engine | Undo | Undo stack for offline | Store prior snapshots or action log; allow undo to previous player-turn boundary. | 2 - Core Game Engine (Rules/State) | Engineering | Offline | P1 | 8 | 2 | T-0017, T-0019 | You+Codex | Backlog | 13 | 2026-02-16 | 2026-02-17 |  | Undo restores exact state; limited by settings.
T-0025 | Engine | Draw | Implement draw-from-deck action | Draw action updates hand and deck; events for animation. | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 6 | 1 | T-0016, T-0017, T-0018 | You+Codex | Backlog | 14 | 2026-02-17 | 2026-02-17 |  | Action validated; reducer updates state; tests cover edge cases.
T-0026 | Engine | Draw | Implement draw-from-discard action | Draw discard respects rule config; updates discard pile. | 2 - Core Game Engine (Rules/State) | Engineering | All | P1 | 6 | 1 | T-0016, T-0017, T-0018 | You+Codex | Backlog | 14 | 2026-02-17 | 2026-02-17 |  | Action validated; reducer updates state; tests cover edge cases.
T-0027 | Engine | Discard | Implement discard action | Discard validates ownership; updates discard; rotates current player. | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 6 | 1 | T-0016, T-0017, T-0018 | You+Codex | Backlog | 14 | 2026-02-17 | 2026-02-17 |  | Action validated; reducer updates state; tests cover edge cases.
T-0028 | Engine | Meld | Implement place-meld action | Validate meld composition under rules; supports jokers/okey usage. | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 10 | 2 | T-0016, T-0017, T-0018 | You+Codex | Backlog | 15 | 2026-02-18 | 2026-02-19 |  | Action validated; reducer updates state; tests cover edge cases.
T-0029 | Engine | Meld | Implement rearrange/extend melds action | Validate table manipulation; event log for UI. | 2 - Core Game Engine (Rules/State) | Engineering | All | P1 | 10 | 2 | T-0016, T-0017, T-0018 | You+Codex | Backlog | 16 | 2026-02-19 | 2026-02-20 |  | Action validated; reducer updates state; tests cover edge cases.
T-0030 | Engine | Round | Implement end-round action | Detect legal finish, compute penalties, start next round or end match. | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 12 | 2 | T-0016, T-0017, T-0018 | You+Codex | Backlog | 17 | 2026-02-20 | 2026-02-21 |  | Action validated; reducer updates state; tests cover edge cases.
T-0031 | Engine | Rules | Implement meld detection utilities | Helpers: find runs/sets in a hand, compute opening points, validate with okey. | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 10 | 2 | T-0016, T-0017 | You+Codex | Backlog | 15 | 2026-02-18 | 2026-02-19 |  | Utilities pass unit tests and used by both rules + AI.
T-0032 | Engine | Rules | Implement indicator/okey logic | Set indicator tile; determine real okey tile; handle fake okey tile behavior. | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 8 | 1.5 | T-0010, T-0001 | You+Codex | Backlog | 9 | 2026-02-12 | 2026-02-13 |  | Correct okey computed for all indicators including edge values.
T-0033 | Engine | Rules | Implement turn/phase state machine | Phases: must_draw, may_meld, must_discard, round_end; enforce via validation. | 2 - Core Game Engine (Rules/State) | Engineering | All | P0 | 8 | 1.5 | T-0016 | You+Codex | Backlog | 9 | 2026-02-12 | 2026-02-13 |  | No illegal phase transitions possible.
T-0034 | Engine | Rules | Implement error reason codes + localization keys | Enumerate validation failure reasons; map to user-facing strings later. | 2 - Core Game Engine (Rules/State) | Engineering | All | P1 | 4 | 1 | T-0016 | You+Codex | Backlog | 12 | 2026-02-15 | 2026-02-15 |  | All validation failures use a reason code.
T-0035 | Offline | Game Setup | Offline game setup screen | Choose player count, bot count, bot difficulty, bot personalities (random default), house rules, match format, timer. | 3 - Offline Gameplay Loop | Engineering | Offline | P0 | 10 | 2 | T-0002, T-0018 | You+Codex | Backlog | 18 | 2026-02-21 | 2026-02-22 |  | User can start offline game with chosen config.
T-0036 | Offline | Controller | Local host game controller | Single-player/offline host applies intents locally; drives UI events. | 3 - Offline Gameplay Loop | Engineering | Offline | P0 | 10 | 2 | T-0017, T-0019 | You+Codex | Backlog | 19 | 2026-02-22 | 2026-02-23 |  | Offline loop supports full game end-to-end without UI polish.
T-0037 | Offline | Undo | Undo button + rules (offline only) | UI + controller integration for undo; block undo after info-revealing steps if needed. | 3 - Offline Gameplay Loop | Engineering | Offline | P1 | 6 | 1 | T-0020 | You+Codex | Backlog | 21 | 2026-02-24 | 2026-02-24 |  | Undo works and is disabled appropriately.
T-0038 | Offline | Persistence | Settings persistence | Save user settings: sound, accessibility, tips shown, last rules preset. | 3 - Offline Gameplay Loop | Engineering | All | P1 | 4 | 1 |  | You+Codex | Backlog | 20 | 2026-02-23 | 2026-02-23 |  | Settings persist between sessions.
T-0039 | Offline | Tips | First-game onboarding tips overlay (skippable) | Guided overlay explaining draw/discard/meld/open; can skip; never forced again. | 3 - Offline Gameplay Loop | Engineering | All | P1 | 8 | 2 | T-0005, T-0033 | You+Codex | Backlog | 21 | 2026-02-24 | 2026-02-25 |  | Tips show once; can be skipped; respects minimal verbosity later.
T-0040 | UI | Framework | Implement UI event bus & state-to-UI binding | Listen to GameState events/deltas; update UI declaratively; avoid logic in view. | 4 - UI/UX & Input | Engineering | All | P0 | 10 | 2 | T-0017 | You+Codex | Backlog | 18 | 2026-02-21 | 2026-02-22 |  | UI updates driven by events; minimal direct state mutation.
T-0041 | UI | Table | Game table layout (landscape) | Create table scene with areas: player hand, meld area, deck/discard, opponent panels. | 4 - UI/UX & Input | Engineering | All | P0 | 12 | 3 | T-0030 | You+Codex | Backlog | 19 | 2026-02-22 | 2026-02-24 |  | Table scales to multiple resolutions; safe margins.
T-0042 | UI | Tiles | Tile visual component | Crisp flat tile art placeholder + numbers/colors; selection states; disabled state. | 4 - UI/UX & Input | Art | All | P0 | 8 | 2 | T-0006 | You+Codex | Backlog | 18 | 2026-02-21 | 2026-02-22 |  | Tile style consistent; readable on mobile.
T-0043 | UI | Input | Tap-select interaction (baseline) | Tap tile to select; buttons to meld/discard; long-press to inspect. | 4 - UI/UX & Input | Engineering | All | P0 | 10 | 2 | T-0032, T-0031 | You+Codex | Backlog | 20 | 2026-02-23 | 2026-02-24 |  | All core actions can be performed without drag.
T-0044 | UI | Input | Drag & drop interaction (optional) | Support dragging tiles to meld area/discard; fallback to tap-select always works. | 4 - UI/UX & Input | Engineering | All | P1 | 12 | 3 | T-0033 | You+Codex | Backlog | 23 | 2026-02-26 | 2026-02-28 |  | Drag works on PC and touch; no accidental drops.
T-0045 | UI | HUD | Action buttons + turn/timer display | Buttons: Draw, Meld/Open, Discard, End Round; show whose turn; timer slider support. | 4 - UI/UX & Input | Engineering | All | P0 | 8 | 2 | T-0030, T-0015 | You+Codex | Backlog | 20 | 2026-02-23 | 2026-02-24 |  | Buttons enable/disable correctly by phase and authority.
T-0046 | UI | Feedback | Toast + error display with verbosity setting | Minimal illegal toast; optional 'Why?' expansion; onboarding overrides verbosity. | 4 - UI/UX & Input | Engineering | All | P1 | 8 | 2 | T-0027, T-0040 | You+Codex | Backlog | 22 | 2026-02-25 | 2026-02-26 |  | Errors are understandable; can be minimal for experienced play.
T-0047 | UI | Animations | Animation system (skippable) | Animate draw/discard/meld; allow tap to skip/fast-forward; keep game snappy. | 4 - UI/UX & Input | Engineering | All | P1 | 12 | 3 | T-0017, T-0031 | You+Codex | Backlog | 24 | 2026-02-27 | 2026-03-01 |  | Animations never block input; skip works; feels 'Balatro snappy'.
T-0048 | UI | Menus | Main menu + navigation | Main menu: Offline, Online, Settings, Credits; simple transitions. | 4 - UI/UX & Input | Engineering | All | P0 | 6 | 1.5 |  | You+Codex | Backlog | 18 | 2026-02-21 | 2026-02-22 |  | All screens reachable; back navigation works on Android.
T-0049 | UI | Menus | Settings screen | Settings: sound, music, tips verbosity, accessibility options, animation speed. | 4 - UI/UX & Input | Engineering | All | P1 | 8 | 2 | T-0029 | You+Codex | Backlog | 22 | 2026-02-25 | 2026-02-26 |  | Settings apply immediately and persist.
T-0050 | UI | Round | Round summary screen | Show scoring breakdown, penalties, cumulative match; next round button. | 4 - UI/UX & Input | Engineering | All | P0 | 8 | 2 | T-0018 | You+Codex | Backlog | 25 | 2026-02-28 | 2026-03-01 |  | Summary matches scoring; readable on mobile.
T-0051 | AI | Framework | Bot seat controller integration | Bots act as players; schedule bot think time; send intents to host controller (offline/online). | 5 - Bots (AI) | Engineering | All | P0 | 8 | 2 | T-0026, T-0017 | You+Codex | Backlog | 22 | 2026-02-25 | 2026-02-26 |  | Bots can take turns in offline game without UI errors.
T-0052 | AI | Heuristics | Hand evaluation scoring function | Compute usefulness score per tile; considers runs/sets potential, seen discards, opening progress. | 5 - Bots (AI) | Engineering | All | P0 | 10 | 2 | T-0025 | You+Codex | Backlog | 23 | 2026-02-26 | 2026-02-27 |  | Function returns stable scores; unit tests for sample hands.
T-0053 | AI | Moves | Meld/open move generator | Generate candidate meld sets for opening and extension; choose best by heuristic. | 5 - Bots (AI) | Engineering | All | P0 | 14 | 3 | T-0025, T-0052 | You+Codex | Backlog | 24 | 2026-02-27 | 2026-03-01 |  | Bot finds obvious melds; respects RuleConfig.
T-0054 | AI | Moves | Discard selection logic | Rank discards; avoid feeding next player; adjust by personality + difficulty. | 5 - Bots (AI) | Engineering | All | P0 | 10 | 2 | T-0052 | You+Codex | Backlog | 25 | 2026-02-28 | 2026-03-01 |  | Bots discard sensibly; difficulty changes behavior.
T-0055 | AI | Difficulty | Difficulty tuning (Easy/Med/Hard) | Tune randomness, search depth, risk thresholds, think delay per difficulty. | 5 - Bots (AI) | Engineering | All | P1 | 8 | 2 | T-0053, T-0054 | You+Codex | Backlog | 27 | 2026-03-02 | 2026-03-03 |  | Difficulty levels feel distinct in playtests.
T-0056 | AI | Personality | Personality profiles (Aggressive/Conservative/Chaotic) | Implement 3 personality weight sets; random by default; optional selection. | 5 - Bots (AI) | Engineering | All | P1 | 6 | 1.5 | T-0052 | You+Codex | Backlog | 27 | 2026-03-02 | 2026-03-03 |  | Personalities visibly differ over multiple rounds.
T-0057 | AI | Testing | Bot regression tests | Simulate many random games headless to detect illegal actions and crashes. | 5 - Bots (AI) | QA | All | P1 | 10 | 2 | T-0015, T-0051 | You+Codex | Backlog | 28 | 2026-03-03 | 2026-03-04 |  | No illegal bot actions; crash-free over N games.
T-0058 | Online | EOS | Add EOS plugin to project | Import EOSG plugin, configure project settings, ensure Windows/Android builds include native libs. | 6 - Online Multiplayer (EOS + P2P) | Engineering | Online | P0 | 8 | 2 | T-0008, T-0011 | You+Codex | Backlog | 24 | 2026-02-27 | 2026-02-28 |  | Project runs with EOS init in editor and exported builds.
T-0059 | Online | EOS | EOS initialization + config loading | Load Product ID/Sandbox/Deployment/Client IDs from config; safe for dev vs release. | 6 - Online Multiplayer (EOS + P2P) | Engineering | Online | P0 | 8 | 2 | T-0058 | You+Codex | Backlog | 25 | 2026-02-28 | 2026-03-01 |  | EOS initializes; errors surfaced; config editable in Settings sheet.
T-0060 | Online | Identity | Guest login via Device ID | Implement Connect DeviceID: create device id if needed, login, display player name prompt. | 6 - Online Multiplayer (EOS + P2P) | Engineering | Online | P0 | 10 | 2 | T-0059 | You+Codex | Backlog | 26 | 2026-03-01 | 2026-03-02 |  | User can play online without Epic account; identity persists per device.
T-0061 | Online | Lobbies | Create lobby (host) with RuleConfig + match settings | Host creates EOS lobby; stores rule hash/config, match format, timer, max players=4. | 6 - Online Multiplayer (EOS + P2P) | Engineering | Online | P0 | 12 | 3 | T-0018, T-0022, T-0060 | You+Codex | Backlog | 27 | 2026-03-02 | 2026-03-04 |  | Lobby created; others can join; metadata correct.
T-0062 | Online | Lobbies | Join lobby + ready system | Client joins via lobby ID/invite code; ready toggles; show players list. | 6 - Online Multiplayer (EOS + P2P) | Engineering | Online | P0 | 12 | 3 | T-0061 | You+Codex | Backlog | 28 | 2026-03-03 | 2026-03-05 |  | Join/leave works; host sees changes; ready gating.
T-0063 | Online | P2P | P2P socket layer for intents/deltas | Build send/receive layer over EOS P2P; reliable ordered channel for turn-based. | 6 - Online Multiplayer (EOS + P2P) | Engineering | Online | P0 | 14 | 3 | T-0019, T-0061, T-0062 | You+Codex | Backlog | 29 | 2026-03-04 | 2026-03-06 |  | Messages delivered; basic latency simulation ok.
T-0064 | Online | Authority | Host-authoritative game controller (online) | Host applies intents, broadcasts deltas; clients only send intents; enforce turn ownership. | 6 - Online Multiplayer (EOS + P2P) | Engineering | Online | P0 | 14 | 3 | T-0017, T-0064 | You+Codex | Backlog | 30 | 2026-03-05 | 2026-03-07 |  | 2-4 players can finish a full match with no desync.
T-0065 | Online | Sync | Snapshot resync & versioning | Add snapshot request/response; include state version; recover from missed deltas. | 6 - Online Multiplayer (EOS + P2P) | Engineering | Online | P0 | 10 | 2 | T-0019, T-0065 | You+Codex | Backlog | 31 | 2026-03-06 | 2026-03-07 |  | Client can resync mid-game; versions monotonically increase.
T-0066 | Online | UI | Online lobby screen UI | Implement lobby UI: create/join, code display, player list, ready, start button (host only). | 6 - Online Multiplayer (EOS + P2P) | Engineering | All | P0 | 10 | 2 | T-0047, T-0061, T-0062 | You+Codex | Backlog | 27 | 2026-03-02 | 2026-03-03 |  | Lobby UI works on PC and Android landscape.
T-0067 | Resilience | Disconnects | Detect disconnects and trigger AI takeover immediately | Monitor EOS lobby member status / P2P timeouts; when peer gone, mark seat AI-controlled instantly. | 7 - Reconnect & Resilience | Engineering | Online | P0 | 10 | 2 | T-0065, T-0051 | You+Codex | Backlog | 32 | 2026-03-07 | 2026-03-08 |  | Game never stalls on disconnect; AI continues legally.
T-0068 | Resilience | Reconnect | Reconnect flow + reclaim on next turn | Returning player rejoins lobby, requests snapshot; seat reclaimed at start of their next turn. | 7 - Reconnect & Resilience | Engineering | Online | P0 | 12 | 3 | T-0066, T-0067 | You+Codex | Backlog | 33 | 2026-03-08 | 2026-03-10 |  | Player can rejoin and resume; no double-control.
T-0069 | Resilience | State | Move log for catch-up | Maintain compact move log (last N actions) to show what happened during disconnect. | 7 - Reconnect & Resilience | Engineering | Online | P1 | 6 | 1.5 | T-0017, T-0065 | You+Codex | Backlog | 34 | 2026-03-09 | 2026-03-10 |  | Returning player sees concise history; log bounded.
T-0070 | Resilience | Timeouts | Timer enforcement + auto-actions | If timer enabled, enforce on host; on timeout choose safe default actions or bot takeover for that turn. | 7 - Reconnect & Resilience | Engineering | Online | P1 | 10 | 2 | T-0040, T-0065 | You+Codex | Backlog | 34 | 2026-03-09 | 2026-03-10 |  | No deadlocks; actions deterministic; UI displays timeout reason.
T-0071 | Resilience | Security | Basic anti-cheat checks | Validate intent sender matches seat; reject illegal deltas; rate-limit spam. | 7 - Reconnect & Resilience | Engineering | Online | P1 | 6 | 1.5 | T-0016, T-0065 | You+Codex | Backlog | 35 | 2026-03-10 | 2026-03-11 |  | Cheat attempts rejected; logs record incidents.
T-0072 | Polish | Audio | Add SFX set (draw/discard/meld/win/lose/UI) | Implement audio bus; volume sliders; add basic SFX placeholders. | 8 - Polish (Audio/Accessibility/Perf) | Audio | All | P1 | 8 | 2 | T-0048 | You+Codex | Backlog | 30 | 2026-03-05 | 2026-03-06 |  | SFX plays; can be muted; no clipping.
T-0073 | Polish | Accessibility | Colorblind-friendly palette option | Alternate tile color palette + patterns/icons; ensure contrast. | 8 - Polish (Audio/Accessibility/Perf) | Engineering | All | P1 | 8 | 2 | T-0032 | You+Codex | Backlog | 31 | 2026-03-06 | 2026-03-07 |  | Colorblind mode toggles; tiles remain distinguishable.
T-0074 | Polish | Accessibility | Large numbers / UI scale option | Option to increase tile label size and UI scaling. | 8 - Polish (Audio/Accessibility/Perf) | Engineering | All | P1 | 6 | 1.5 | T-0032 | You+Codex | Backlog | 31 | 2026-03-06 | 2026-03-07 |  | Text readable on small phones; no overlap.
T-0075 | Polish | Performance | Optimize tile rendering & pooling | Pool tile nodes; avoid layout thrash; keep 60fps on mid Android. | 8 - Polish (Audio/Accessibility/Perf) | Engineering | All | P1 | 10 | 2 | T-0032, T-0042 | You+Codex | Backlog | 33 | 2026-03-08 | 2026-03-09 |  | Stable FPS; memory allocations reduced.
T-0076 | Polish | UX | Animation speed settings (Normal/Fast/Off) | Let users control animation pacing; keep defaults snappy. | 8 - Polish (Audio/Accessibility/Perf) | Engineering | All | P2 | 4 | 1 | T-0042, T-0048 | You+Codex | Backlog | 32 | 2026-03-07 | 2026-03-07 |  | Setting affects all animations; no desync online.
T-0077 | Polish | Art | Finalize tile art (flat crisp) | Replace placeholder tiles with final vector-style assets; ensure readability. | 8 - Polish (Audio/Accessibility/Perf) | Art | All | P1 | 12 | 3 | T-0032, T-0006 | You+Codex | Backlog | 32 | 2026-03-07 | 2026-03-09 |  | Final tiles in-game; consistent style across UI.
T-0078 | Polish | UX | In-game help screen (rules summary) | Short rules summary and controls help accessible from pause menu. | 8 - Polish (Audio/Accessibility/Perf) | Writing | All | P2 | 6 | 1.5 | T-0001 | You+Codex | Backlog | 34 | 2026-03-09 | 2026-03-10 |  | Help is concise and accurate; accessible offline and online.
T-0079 | QA | Matrix | Create test matrix (PC/Android; Offline/Online; 2-4p) | Define test cases covering setup, actions, scoring, disconnects, timers, undo. | 9 - QA & Test Matrix | QA | All | P0 | 8 | 2 | T-0001, T-0004 | You+Codex | Backlog | 34 | 2026-03-09 | 2026-03-10 |  | Matrix covers all core features; prioritized smoke list exists.
T-0080 | QA | Rules | Automated rules unit tests | Create sample hands/rounds to assert validation and scoring. | 9 - QA & Test Matrix | QA | All | P0 | 14 | 3 | T-0016, T-0018 | You+Codex | Backlog | 35 | 2026-03-10 | 2026-03-12 |  | Tests pass; catch regressions; run in CI or locally.
T-0081 | QA | Online | Multiplayer soak tests | Simulate games with random intents; packet loss; reconnects; long sessions. | 9 - QA & Test Matrix | QA | Online | P1 | 12 | 3 | T-0065, T-0067 | You+Codex | Backlog | 36 | 2026-03-11 | 2026-03-13 |  | No desync; no crashes after N matches.
T-0082 | QA | UX | Playtest pass & balancing notes | Human playtests: fun factor, bot personalities, timer defaults, UI friction. | 9 - QA & Test Matrix | QA | All | P1 | 10 | 2 | T-0056, T-0042 | You+Codex | Backlog | 37 | 2026-03-12 | 2026-03-13 |  | Actionable list of changes; top 10 issues fixed.
T-0083 | QA | Bugs | Bug triage board + release criteria | Define P0/P1 bug criteria; ship checklist; crash-free requirements. | 9 - QA & Test Matrix | QA | All | P1 | 4 | 1 |  | You+Codex | Backlog | 37 | 2026-03-12 | 2026-03-12 |  | Release checklist exists; bugs categorized and tracked.
T-0084 | Release | Builds | Automated build scripts | Create scripts for version bumping, exporting PC + Android builds, zipping artifacts. | 10 - Builds & Release Pipeline | DevOps | All | P1 | 8 | 2 | T-0008, T-0009 | You+Codex | Backlog | 38 | 2026-03-13 | 2026-03-14 |  | One command produces exports; version embedded.
T-0085 | Release | Android | Android signing + AAB/APK generation | Finalize keystore; configure gradle; generate signed AAB/APK. | 10 - Builds & Release Pipeline | DevOps | Android | P1 | 6 | 1.5 | T-0008 | You+Codex | Backlog | 39 | 2026-03-14 | 2026-03-15 |  | Signed build installs; Play Console upload check passes.
T-0086 | Release | PC | Windows/Linux packaging | Create release folder structure; include licenses; optional installer later. | 10 - Builds & Release Pipeline | DevOps | PC | P2 | 4 | 1 | T-0009 | You+Codex | Backlog | 39 | 2026-03-14 | 2026-03-14 |  | PC builds run on clean machine; no missing DLLs.
T-0087 | Release | Telemetry | Crash reporting plan (optional) | Decide if any crash reporting is used; if none, ensure logs accessible. | 10 - Builds & Release Pipeline | Design | All | P2 | 3 | 0.5 |  | You+Codex | Backlog | 38 | 2026-03-13 | 2026-03-13 |  | Decision recorded; privacy impact understood.
T-0088 | Release | Versioning | Changelog + semantic versioning | Define version scheme; maintain changelog; embed build number in UI. | 10 - Builds & Release Pipeline | Writing | All | P2 | 4 | 1 |  | You+Codex | Backlog | 38 | 2026-03-13 | 2026-03-13 |  | Version visible in settings; changelog maintained.
T-0089 | Store | Assets | Create app icon + feature graphic | Design icon consistent with flat style; export required sizes. | 11 - Store/Distribution Prep | Art | All | P1 | 8 | 2 | T-0083 | You+Codex | Backlog | 40 | 2026-03-15 | 2026-03-16 |  | Icon meets platform guidelines; readable at small size.
T-0090 | Store | Assets | Capture screenshots + short trailer (optional) | Take PC + Android screenshots; record 10-20s clip; add captions. | 11 - Store/Distribution Prep | Art | All | P2 | 10 | 2 | T-0078, T-0065 | You+Codex | Backlog | 41 | 2026-03-16 | 2026-03-17 |  | Screenshots cover key features; no placeholder art.
T-0091 | Store | Copy | Write store description (PC + Android) | Short description, feature bullets, online/offline details, rule variants. | 11 - Store/Distribution Prep | Writing | All | P1 | 6 | 1.5 | T-0001, T-0061 | You+Codex | Backlog | 41 | 2026-03-16 | 2026-03-17 |  | Copy is clear; no misleading claims.
T-0092 | Store | Legal | Privacy policy + EOS disclosure | Draft privacy policy explaining data usage (EOS services, device id). | 11 - Store/Distribution Prep | Writing | Online | P1 | 6 | 1.5 | T-0060 | You+Codex | Backlog | 41 | 2026-03-16 | 2026-03-17 |  | Policy ready; store listing references it.
T-0093 | Store | Release | Beta distribution plan | Plan closed beta/testflight-style for Android; itch.io beta for PC. | 11 - Store/Distribution Prep | Design | All | P2 | 4 | 1 |  | You+Codex | Backlog | 40 | 2026-03-15 | 2026-03-15 |  | Beta steps documented; testers invited.
Formulas:
Start Date = Settings!$B4+[Start Offset (d)]
End Date = [Start Date]+ROUNDUP([Est (days)],0)-1

## Stage Plan
Stage | Stage Start | Stage End | Start Offset (d) | Duration (d)
0 - Preproduction (Spec & Design Lock) | 2026-02-03 | 2026-02-06 | 0 | 4
1 - Project Setup & Tooling | 2026-02-07 | 2026-02-09 | 4 | 3
2 - Core Game Engine (Rules/State) | 2026-02-10 | 2026-02-21 | 7 | 12
3 - Offline Gameplay Loop | 2026-02-21 | 2026-02-25 | 18 | 5
4 - UI/UX & Input | 2026-02-21 | 2026-03-01 | 18 | 9
5 - Bots (AI) | 2026-02-25 | 2026-03-04 | 22 | 8
6 - Online Multiplayer (EOS + P2P) | 2026-02-27 | 2026-03-07 | 24 | 9
8 - Polish (Audio/Accessibility/Perf) | 2026-03-05 | 2026-03-10 | 30 | 6
7 - Reconnect & Resilience | 2026-03-07 | 2026-03-11 | 32 | 5
9 - QA & Test Matrix | 2026-03-09 | 2026-03-13 | 34 | 5
10 - Builds & Release Pipeline | 2026-03-13 | 2026-03-15 | 38 | 3
11 - Store/Distribution Prep | 2026-03-15 | 2026-03-17 | 40 | 3

## Gantt
Stage Gantt (based on Start Offset + Duration)
Stage | Start Offset (d) | Duration (d)
0 - Preproduction (Spec & Design Lock) | 0 | 4
1 - Project Setup & Tooling | 4 | 3
2 - Core Game Engine (Rules/State) | 7 | 12
3 - Offline Gameplay Loop | 18 | 5
4 - UI/UX & Input | 18 | 9
5 - Bots (AI) | 22 | 8
6 - Online Multiplayer (EOS + P2P) | 24 | 9
8 - Polish (Audio/Accessibility/Perf) | 30 | 6
7 - Reconnect & Resilience | 32 | 5
9 - QA & Test Matrix | 34 | 5
10 - Builds & Release Pipeline | 38 | 3
11 - Store/Distribution Prep | 40 | 3

## Dashboard
Dashboard
Tasks by Status
Status | Count
Backlog | 93
Planned | 0
In Progress | 0
Blocked | 0
Review | 0
Done | 0
Tasks by Stage
Stage | Count
0 - Preproduction (Spec & Design Lock) | 7
1 - Project Setup & Tooling | 7
2 - Core Game Engine (Rules/State) | 20
3 - Offline Gameplay Loop | 5
4 - UI/UX & Input | 11
5 - Bots (AI) | 7
6 - Online Multiplayer (EOS + P2P) | 9
7 - Reconnect & Resilience | 5
8 - Polish (Audio/Accessibility/Perf) | 7
9 - QA & Test Matrix | 5
10 - Builds & Release Pipeline | 5
11 - Store/Distribution Prep | 5