## Task Master List
Task ID | Phase | Task Name | Duration (Days) | Start Date | End Date | Dependencies | Status | Assigned To | Priority | Completion % | Notes | Issues
1.1 | Phase 1: Foundation & Architecture | Project Setup & Repository Structure | 1 | 2026-02-09 | 2026-02-09 | None | Not Started | Codex | High | 0
1.2 | Phase 1: Foundation & Architecture | Define RuleConfig Schema (JSON) | 2 | 2026-02-10 | 2026-02-11 | 1.1 | Not Started | Codex | High | 0
1.3 | Phase 1: Foundation & Architecture | Create Core State Model (GameState class) | 2 | 2026-02-10 | 2026-02-11 | 1.1 | Not Started | Codex | High | 0
1.4 | Phase 1: Foundation & Architecture | Implement Action API (enum + validation) | 2 | 2026-02-12 | 2026-02-13 | 1.3 | Not Started | Codex | High | 0
2.1 | Phase 2: Game Logic Core | Tile System (numbers, colors, jokers) | 2 | 2026-02-14 | 2026-02-15 | 1.3 | Not Started | Codex | High | 0
2.2 | Phase 2: Game Logic Core | Hand Management (draw, discard, sort) | 2 | 2026-02-16 | 2026-02-17 | 2.1 | Not Started | Codex | High | 0
2.3 | Phase 2: Game Logic Core | Meld Validation (sets, runs) | 3 | 2026-02-18 | 2026-02-20 | 2.2 | Not Started | Codex | High | 0
2.4 | Phase 2: Game Logic Core | Opening Logic (point threshold) | 2 | 2026-02-21 | 2026-02-22 | 2.3 | Not Started | Codex | High | 0
2.5 | Phase 2: Game Logic Core | Win Condition & Scoring System | 2 | 2026-02-23 | 2026-02-24 | 2.4 | Not Started | Codex | High | 0
2.6 | Phase 2: Game Logic Core | Turn Timer Implementation | 1 | 2026-02-14 | 2026-02-14 | 1.4 | Not Started | Codex | High | 0
3.1 | Phase 3: Bot AI | Bot Base Class & Interface | 1 | 2026-02-25 | 2026-02-25 | 2.5 | Not Started | Codex | Medium | 0
3.2 | Phase 3: Bot AI | Easy Bot (random valid moves) | 2 | 2026-02-26 | 2026-02-27 | 3.1 | Not Started | Codex | Medium | 0
3.3 | Phase 3: Bot AI | Medium Bot (heuristic evaluation) | 3 | 2026-02-28 | 2026-03-02 | 3.2 | Not Started | Codex | Medium | 0
3.4 | Phase 3: Bot AI | Hard Bot (lookahead + optimization) | 3 | 2026-03-03 | 2026-03-05 | 3.3 | Not Started | Codex | Medium | 0
3.5 | Phase 3: Bot AI | Personality System (Aggressive/Conservative/Chaotic) | 2 | 2026-03-06 | 2026-03-07 | 3.4 | Not Started | Codex | Medium | 0
4.1 | Phase 4: UI Foundation | Scene Structure & Navigation | 1 | 2026-03-08 | 2026-03-08 | 1.1 | Not Started | Codex | Medium | 0
4.2 | Phase 4: UI Foundation | Tile Sprite Design & Assets | 2 | 2026-03-09 | 2026-03-10 | 4.1 | Not Started | Codex | Medium | 0
4.3 | Phase 4: UI Foundation | Table Layout (4-player positions) | 2 | 2026-03-11 | 2026-03-12 | 4.2 | Not Started | Codex | Medium | 0
4.4 | Phase 4: UI Foundation | Hand Display & Sorting UI | 2 | 2026-03-13 | 2026-03-14 | 4.3 | Not Started | Codex | Medium | 0
4.5 | Phase 4: UI Foundation | Action Buttons (Draw/Discard/Open/Finish) | 1 | 2026-03-15 | 2026-03-15 | 4.4 | Not Started | Codex | Medium | 0
5.1 | Phase 5: UI Interactions | Tap-to-Select Tile System | 2 | 2026-03-16 | 2026-03-17 | 4.5 | Not Started | Codex | Medium | 0
5.2 | Phase 5: UI Interactions | Drag-and-Drop (optional enhancement) | 2 | 2026-03-18 | 2026-03-19 | 5.1 | Not Started | Codex | Medium | 0
5.3 | Phase 5: UI Interactions | Meld Display & Organization | 2 | 2026-03-18 | 2026-03-19 | 5.1 | Not Started | Codex | Medium | 0
5.4 | Phase 5: UI Interactions | Animation System (draw/discard/move) | 2 | 2026-03-20 | 2026-03-21 | 5.3 | Not Started | Codex | Medium | 0
5.5 | Phase 5: UI Interactions | Feedback System (illegal move messages) | 1 | 2026-03-18 | 2026-03-18 | 5.1 | Not Started | Codex | Medium | 0
5.6 | Phase 5: UI Interactions | Undo System (offline only) | 1 | 2026-03-15 | 2026-03-15 | 2.5 | Not Started | Codex | Medium | 0
6.1 | Phase 6: Offline Mode | Local Game Controller | 1 | 2026-03-22 | 2026-03-22 | 5.5 | Not Started | Codex | Medium | 0
6.2 | Phase 6: Offline Mode | Bot Integration & Seat Management | 2 | 2026-03-23 | 2026-03-24 | 3.5, 6.1 | Not Started | Codex | Medium | 0
6.3 | Phase 6: Offline Mode | Settings Menu (Rules/Bots/Timer) | 2 | 2026-03-25 | 2026-03-26 | 6.2 | Not Started | Codex | Medium | 0
6.4 | Phase 6: Offline Mode | Game Replay System | 2 | 2026-03-23 | 2026-03-24 | 6.1 | Not Started | Codex | Medium | 0
7.1 | Phase 7: Online Networking | EOS SDK Integration (Godot plugin) | 2 | 2026-03-27 | 2026-03-28 | 1.1 | Not Started | Codex | Medium | 0
7.2 | Phase 7: Online Networking | Guest/DeviceID Authentication | 2 | 2026-03-29 | 2026-03-30 | 7.1 | Not Started | Codex | Medium | 0
7.3 | Phase 7: Online Networking | Lobby Create/Join System | 2 | 2026-03-31 | 2026-04-01 | 7.2 | Not Started | Codex | Medium | 0
7.4 | Phase 7: Online Networking | Host-Authoritative Action Sync | 3 | 2026-04-02 | 2026-04-04 | 7.3, 1.4 | Not Started | Codex | Medium | 0
7.5 | Phase 7: Online Networking | State Resync Mechanism | 2 | 2026-04-05 | 2026-04-06 | 7.4 | Not Started | Codex | Medium | 0
7.6 | Phase 7: Online Networking | Reconnect + Bot Takeover | 2 | 2026-04-07 | 2026-04-08 | 7.5 | Not Started | Codex | Medium | 0
8.1 | Phase 8: Polish & Testing | Sound Effects & Music | 2 | 2026-04-09 | 2026-04-10 | 5.4 | Not Started | Codex | Medium | 0
8.2 | Phase 8: Polish & Testing | Accessibility (colorblind mode, large text) | 2 | 2026-04-09 | 2026-04-10 | 4.2 | Not Started | Codex | Medium | 0
8.3 | Phase 8: Polish & Testing | Bug Fixing & Edge Cases | 3 | 2026-04-09 | 2026-04-11 | 7.6, 6.4 | Not Started | Codex | Medium | 0
8.4 | Phase 8: Polish & Testing | Performance Optimization (Android) | 2 | 2026-04-12 | 2026-04-13 | 8.3 | Not Started | Codex | Medium | 0
8.5 | Phase 8: Polish & Testing | Tutorial/Onboarding Flow | 2 | 2026-04-09 | 2026-04-10 | 6.3 | Not Started | Codex | Medium | 0
9.1 | Phase 9: Release Preparation | Android APK Build & Testing | 1 | 2026-04-14 | 2026-04-14 | 8.4 | Not Started | Codex | Medium | 0
9.2 | Phase 9: Release Preparation | PC Build & Testing | 1 | 2026-04-14 | 2026-04-14 | 8.4 | Not Started | Codex | Medium | 0
9.3 | Phase 9: Release Preparation | Final QA & Stress Testing | 2 | 2026-04-15 | 2026-04-16 | 9.1, 9.2 | Not Started | Codex | Medium | 0
9.4 | Phase 9: Release Preparation | Documentation & README | 1 | 2026-04-17 | 2026-04-17 | 9.3 | Not Started | Codex | Medium | 0

## Gantt Chart
Task ID | Task Name | Duration | 02/09 | 02/16 | 02/23 | 03/02 | 03/09 | 03/16 | 03/23 | 03/30 | 04/06 | 04/13
1.1 | Project Setup & Repository Structure | 1 | █
1.2 | Define RuleConfig Schema (JSON) | 2 | █
1.3 | Create Core State Model (GameState class) | 2 | █
1.4 | Implement Action API (enum + validation) | 2 | █
2.1 | Tile System (numbers, colors, jokers) | 2 | █
2.2 | Hand Management (draw, discard, sort) | 2 |  | █
2.3 | Meld Validation (sets, runs) | 3 |  | █
2.4 | Opening Logic (point threshold) | 2 |  | █
2.5 | Win Condition & Scoring System | 2 |  |  | █
2.6 | Turn Timer Implementation | 1 | █
3.1 | Bot Base Class & Interface | 1 |  |  | █
3.2 | Easy Bot (random valid moves) | 2 |  |  | █
3.3 | Medium Bot (heuristic evaluation) | 3 |  |  | █ | █
3.4 | Hard Bot (lookahead + optimization) | 3 |  |  |  | █
3.5 | Personality System (Aggressive/Conservative/Chaotic) | 2 |  |  |  | █
4.1 | Scene Structure & Navigation | 1 |  |  |  | █
4.2 | Tile Sprite Design & Assets | 2 |  |  |  |  | █
4.3 | Table Layout (4-player positions) | 2 |  |  |  |  | █
4.4 | Hand Display & Sorting UI | 2 |  |  |  |  | █
4.5 | Action Buttons (Draw/Discard/Open/Finish) | 1 |  |  |  |  | █
5.1 | Tap-to-Select Tile System | 2 | [5 empty] | █
5.2 | Drag-and-Drop (optional enhancement) | 2 | [5 empty] | █
5.3 | Meld Display & Organization | 2 | [5 empty] | █
5.4 | Animation System (draw/discard/move) | 2 | [5 empty] | █
5.5 | Feedback System (illegal move messages) | 1 | [5 empty] | █
5.6 | Undo System (offline only) | 1 |  |  |  |  | █
6.1 | Local Game Controller | 1 | [5 empty] | █
6.2 | Bot Integration & Seat Management | 2 | [6 empty] | █
6.3 | Settings Menu (Rules/Bots/Timer) | 2 | [6 empty] | █
6.4 | Game Replay System | 2 | [6 empty] | █
7.1 | EOS SDK Integration (Godot plugin) | 2 | [6 empty] | █
7.2 | Guest/DeviceID Authentication | 2 | [6 empty] | █ | █
7.3 | Lobby Create/Join System | 2 | [7 empty] | █
7.4 | Host-Authoritative Action Sync | 3 | [7 empty] | █
7.5 | State Resync Mechanism | 2 | [7 empty] | █ | █
7.6 | Reconnect + Bot Takeover | 2 | [8 empty] | █
8.1 | Sound Effects & Music | 2 | [8 empty] | █
8.2 | Accessibility (colorblind mode, large text) | 2 | [8 empty] | █
8.3 | Bug Fixing & Edge Cases | 3 | [8 empty] | █
8.4 | Performance Optimization (Android) | 2 | [8 empty] | █ | █
8.5 | Tutorial/Onboarding Flow | 2 | [8 empty] | █
9.1 | Android APK Build & Testing | 1 | [9 empty] | █
9.2 | PC Build & Testing | 1 | [9 empty] | █
9.3 | Final QA & Stress Testing | 2 | [9 empty] | █
9.4 | Documentation & README | 1 | [9 empty] | █

## Phase Summary
Phase | Total Tasks | Total Duration (Days) | Start Date | End Date | Status
Phase 1: Foundation & Architecture | 4 | 7 | 2026-02-09 | 2026-02-13 | Not Started
Phase 2: Game Logic Core | 6 | 12 | 2026-02-14 | 2026-02-24 | Not Started
Phase 3: Bot AI | 5 | 11 | 2026-02-25 | 2026-03-07 | Not Started
Phase 4: UI Foundation | 5 | 8 | 2026-03-08 | 2026-03-15 | Not Started
Phase 5: UI Interactions | 6 | 10 | 2026-03-16 | 2026-03-21 | Not Started
Phase 6: Offline Mode | 4 | 7 | 2026-03-22 | 2026-03-26 | Not Started
Phase 7: Online Networking | 6 | 13 | 2026-03-27 | 2026-04-08 | Not Started
Phase 8: Polish & Testing | 5 | 11 | 2026-04-09 | 2026-04-13 | Not Started
Phase 9: Release Preparation | 4 | 5 | 2026-04-14 | 2026-04-17 | Not Started

## Codex Prompts
Task ID | Prompt Template for Codex
1.1 | Task: Project Setup & Repository Structure Context: - Part of Phase 1: Foundation & Architecture - Duration: 1 days - Dependencies: None Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
1.2 | Task: Define RuleConfig Schema (JSON) Context: - Part of Phase 1: Foundation & Architecture - Duration: 2 days - Dependencies: 1.1 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
1.3 | Task: Create Core State Model (GameState class) Context: - Part of Phase 1: Foundation & Architecture - Duration: 2 days - Dependencies: 1.1 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
1.4 | Task: Implement Action API (enum + validation) Context: - Part of Phase 1: Foundation & Architecture - Duration: 2 days - Dependencies: 1.3 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
2.1 | Task: Tile System (numbers, colors, jokers) Context: - Part of Phase 2: Game Logic Core - Duration: 2 days - Dependencies: 1.3 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
2.2 | Task: Hand Management (draw, discard, sort) Context: - Part of Phase 2: Game Logic Core - Duration: 2 days - Dependencies: 2.1 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
2.3 | Task: Meld Validation (sets, runs) Context: - Part of Phase 2: Game Logic Core - Duration: 3 days - Dependencies: 2.2 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
2.4 | Task: Opening Logic (point threshold) Context: - Part of Phase 2: Game Logic Core - Duration: 2 days - Dependencies: 2.3 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
2.5 | Task: Win Condition & Scoring System Context: - Part of Phase 2: Game Logic Core - Duration: 2 days - Dependencies: 2.4 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
2.6 | Task: Turn Timer Implementation Context: - Part of Phase 2: Game Logic Core - Duration: 1 days - Dependencies: 1.4 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
3.1 | Task: Bot Base Class & Interface Context: - Part of Phase 3: Bot AI - Duration: 1 days - Dependencies: 2.5 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
3.2 | Task: Easy Bot (random valid moves) Context: - Part of Phase 3: Bot AI - Duration: 2 days - Dependencies: 3.1 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
3.3 | Task: Medium Bot (heuristic evaluation) Context: - Part of Phase 3: Bot AI - Duration: 3 days - Dependencies: 3.2 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
3.4 | Task: Hard Bot (lookahead + optimization) Context: - Part of Phase 3: Bot AI - Duration: 3 days - Dependencies: 3.3 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
3.5 | Task: Personality System (Aggressive/Conservative/Chaotic) Context: - Part of Phase 3: Bot AI - Duration: 2 days - Dependencies: 3.4 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
4.1 | Task: Scene Structure & Navigation Context: - Part of Phase 4: UI Foundation - Duration: 1 days - Dependencies: 1.1 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
4.2 | Task: Tile Sprite Design & Assets Context: - Part of Phase 4: UI Foundation - Duration: 2 days - Dependencies: 4.1 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
4.3 | Task: Table Layout (4-player positions) Context: - Part of Phase 4: UI Foundation - Duration: 2 days - Dependencies: 4.2 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
4.4 | Task: Hand Display & Sorting UI Context: - Part of Phase 4: UI Foundation - Duration: 2 days - Dependencies: 4.3 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
4.5 | Task: Action Buttons (Draw/Discard/Open/Finish) Context: - Part of Phase 4: UI Foundation - Duration: 1 days - Dependencies: 4.4 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
5.1 | Task: Tap-to-Select Tile System Context: - Part of Phase 5: UI Interactions - Duration: 2 days - Dependencies: 4.5 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
5.2 | Task: Drag-and-Drop (optional enhancement) Context: - Part of Phase 5: UI Interactions - Duration: 2 days - Dependencies: 5.1 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
5.3 | Task: Meld Display & Organization Context: - Part of Phase 5: UI Interactions - Duration: 2 days - Dependencies: 5.1 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
5.4 | Task: Animation System (draw/discard/move) Context: - Part of Phase 5: UI Interactions - Duration: 2 days - Dependencies: 5.3 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
5.5 | Task: Feedback System (illegal move messages) Context: - Part of Phase 5: UI Interactions - Duration: 1 days - Dependencies: 5.1 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
5.6 | Task: Undo System (offline only) Context: - Part of Phase 5: UI Interactions - Duration: 1 days - Dependencies: 2.5 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
6.1 | Task: Local Game Controller Context: - Part of Phase 6: Offline Mode - Duration: 1 days - Dependencies: 5.5 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
6.2 | Task: Bot Integration & Seat Management Context: - Part of Phase 6: Offline Mode - Duration: 2 days - Dependencies: 3.5, 6.1 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
6.3 | Task: Settings Menu (Rules/Bots/Timer) Context: - Part of Phase 6: Offline Mode - Duration: 2 days - Dependencies: 6.2 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
6.4 | Task: Game Replay System Context: - Part of Phase 6: Offline Mode - Duration: 2 days - Dependencies: 6.1 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
7.1 | Task: EOS SDK Integration (Godot plugin) Context: - Part of Phase 7: Online Networking - Duration: 2 days - Dependencies: 1.1 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
7.2 | Task: Guest/DeviceID Authentication Context: - Part of Phase 7: Online Networking - Duration: 2 days - Dependencies: 7.1 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
7.3 | Task: Lobby Create/Join System Context: - Part of Phase 7: Online Networking - Duration: 2 days - Dependencies: 7.2 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
7.4 | Task: Host-Authoritative Action Sync Context: - Part of Phase 7: Online Networking - Duration: 3 days - Dependencies: 7.3, 1.4 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
7.5 | Task: State Resync Mechanism Context: - Part of Phase 7: Online Networking - Duration: 2 days - Dependencies: 7.4 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
7.6 | Task: Reconnect + Bot Takeover Context: - Part of Phase 7: Online Networking - Duration: 2 days - Dependencies: 7.5 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
8.1 | Task: Sound Effects & Music Context: - Part of Phase 8: Polish & Testing - Duration: 2 days - Dependencies: 5.4 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
8.2 | Task: Accessibility (colorblind mode, large text) Context: - Part of Phase 8: Polish & Testing - Duration: 2 days - Dependencies: 4.2 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
8.3 | Task: Bug Fixing & Edge Cases Context: - Part of Phase 8: Polish & Testing - Duration: 3 days - Dependencies: 7.6, 6.4 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
8.4 | Task: Performance Optimization (Android) Context: - Part of Phase 8: Polish & Testing - Duration: 2 days - Dependencies: 8.3 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
8.5 | Task: Tutorial/Onboarding Flow Context: - Part of Phase 8: Polish & Testing - Duration: 2 days - Dependencies: 6.3 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
9.1 | Task: Android APK Build & Testing Context: - Part of Phase 9: Release Preparation - Duration: 1 days - Dependencies: 8.4 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
9.2 | Task: PC Build & Testing Context: - Part of Phase 9: Release Preparation - Duration: 1 days - Dependencies: 8.4 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
9.3 | Task: Final QA & Stress Testing Context: - Part of Phase 9: Release Preparation - Duration: 2 days - Dependencies: 9.1, 9.2 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]
9.4 | Task: Documentation & README Context: - Part of Phase 9: Release Preparation - Duration: 1 days - Dependencies: 9.3 Requirements: [Specific requirements based on task - to be filled in during execution] Deliverables: [Expected code files, functions, or features - to be defined] Technical Constraints: - Godot 4.x GDScript - Follow project architecture (see docs/ARCHITECTURE.md) - Ensure compatibility with both PC and Android - Write testable, modular code Implementation Notes: [Add specific notes as needed]

## Daily Progress
Date | Tasks Completed | Tasks In Progress | Blockers | Notes